## Sheet1
#	Type	Priority	Status	Title	Description and comments	Estimated [h]	Actual [h]	Who	Date created	Date closed
	feat	3 [high]	OPEN
	fix	2 [medium]	WORK-IN-PROGRESS
	docs	1 [low]	CLOSED
	style
	refactor
	perf
	test
	chore
	build
	ci

1	refactor	2 [medium]	CLOSED		Clean
2	feat	2 [medium]	CLOSED		Architecture functional core + endpoints
3	chore	2 [medium]	CLOSED		setup.py qui installe des executables (à la PyFoam)
4	feat	2 [medium]	CLOSED		Type hints + strings formatting
5	feat	2 [medium]	CLOSED		Trim and heave
6	feat	2 [medium]	CLOSED		Graceful exceptions handling
7	feat	2 [medium]	CLOSED		Pre-canned y+ computations for air and water
8	feat	2 [medium]	CLOSED		récupérer les calculs de tailles de cellules de fullmar_cases (zones.py) pour aaFoam
9	feat	2 [medium]	CLOSED		Function that retrieves forces (call by code, not an executable) and averages over last n iterations
10	test	2 [medium]	OPEN	Tests	Add them !
11	feat	2 [medium]	OPEN		aaForcesWatcher*.py / aaFoamCoefsWatcher.py / Live change of params (tkinter UI? interprocess com?) / If building a more elaborate UI, use tkinter (included with Python, no cumbersome PyQt of Wx installs)
12	feat	2 [medium]	CLOSED		aaFoamVL -> VL = Viscous layers -> outer cell thickness and total thickness / From first layer thickness, progression and expansion ratio
13	feat	2 [medium]	CLOSED		aaFoamYPlus -> Y+ calculator (same as Pointwise online calc)
14	feat	2 [medium]	OPEN		Memory usage of a case -> see _Repositories/wip/ps_mem
15	feat	2 [medium]	OPEN		aaFoamGrading -> grading calculations for blockMesh (same as online)
16	feat	2 [medium]	OPEN		aaFoamFrictionLines -> theoretical friction line computations to check against CFD results
17	feat	2 [medium]	OPEN		aaFoamBL -> theoretical BL thickness
18	feat	2 [medium]	OPEN		real pressure in incompressible flow (aaFoamMult) : p file -> p_real file